## Sheet1
PROJECT Name - Task List & Estimation
Sl. |  | Interval ID | Task list | Estimated Dev Hours | Remaining Dev Hours | Estimated QA Hours | R&D Hours | Status | DEV | QA | Remarks
1 | Complain Management System
| 1.1 |  | User wise login system | 32 |  |  |  | Ongoing
| 1.2 |  | Complain receive form | 32
| 1.3 |  | Complaiin receive sms function
| 1.4 |  | Complain history manage
| 1.5 |  | Complain solved sms
| 1.6 |  | Report Generateion
| 1.7 |  | Manual Complain Entry Sheet Division Wise
64
2 | Knowledge Portal
| 2.1 |  | Admin Login System | 40
| 2.2 |  | FAQ Module | 40 |  |  |  | Ongoing
| 2.3 |  | Product Module | 24
| 2.4 |  | Showroom Module
| 2.5 |  | Mail Configuration
| 2.6 |  | Frontend Site design to show Individual Module Item
| 2.7 |  | Frontend Site Searching
| 2.8 |  | Backend: In product module, Implementing pdf, excel and image
104
3 | Customer Information
| 3.1 |  | Division Wise Customer Informarion | 56
| 3.2 |  | Customer history Management | 80 |  |  |  | Ongoing
| 3.3 |  | Report Generateion | 40
176
4 | HR API
| 4.1 |  | sql database implementing | 2
| 4.2 |  | API Development for communication with Main DB | 4
| 4.3 |  | Dashbiard according the requirement from ERP
6
5 | Corporate Web Site
| 5.1 |  | Full site development | 240 |  |  |  | Ongoing
240
6 | KICD Software
| 6.1 |  | Existing application review and implement the new requirements | 240 |  |  |  | Ongoing
240
7 | Interactive Anlytical Data Dashboard report Management for CTG Port
| 7.1 |  | Live data with interctive chart implementation | 240
240
8 | Container status SMS notification in CTG
| 81 |  |  | 240 |  |  |  | Done
240
9 | Saif Sporting Club
| 9.1 |  |  | 360 |  |  |  | Done
360
10 | Saif Battery Machine QR Code generation
| 10.1 |  |  | 36 |  |  |  | Done
36